## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (actual date) | Date finished (actual date)
US1 | Manual Transaction Entry | As a user, I want to manually input my income and expenses so that I can track my financial transactions. | Must Have | Iteration 1 | - Users can enter transaction details (amount, category, date, description). | 5 |  | 2025-03-18 | 2025-03-22
- System saves transactions correctly in a file.
- Transactions can be listed and viewed later.
US2 | Import Transactions from File | As a user, I want to import transactions from a CSV or JSON file so that I don’t have to input them manually. | Must Have | Iteration 1 | - System reads and parses CSV/JSON files. | 8 |  | 2025-03-22 | 2025-03-26
- Transactions are displayed after import.
- System detects and handles incorrect formats.
US3 | Edit and Delete Transactions | As a user, I want to edit and delete transactions so that I can correct mistakes. | Must Have | Iteration 2 | - Users can select a transaction and update details. | 5 |  | 2025-03-22 | 2025-03-27
- Users can delete a transaction from the list.
- Changes are saved correctly in the file.
US4 | Automatic Expense Categorization | As a user, I want transactions to be automatically categorized so that I don’t have to manually assign categories. | Must Have | Iteration 2 | - System assigns categories based on keywords or rules. | 5 |  | 2025-03-28 | 2025-04-02
- Users can override and correct misclassified transactions.
US5 | Manual Category Adjustment | As a user, I want to manually modify the category of transactions so that I can ensure accurate classification. | Should Have | Iteration 2 | - Users can change the assigned category.
[5 empty] | - System updates and saves changes persistently. | 8 |  | 2025-04-02 | 2025-04-10
US6 | Set Monthly Budget | As a user, I want to set a monthly budget for different expense categories so that I can manage my spending effectively. | Must Have | Iteration 3 | - Users can set budget limits per category.
[5 empty] | - Budget data is saved in a file. | 3 |  | 2025-04-10 | 2025-04-14
- Users can edit and delete budgets.
US7 | Track Expenses Against Budget | As a user, I want to view my current expenses against my budget so that I can track my spending. | Must Have | Iteration 3 | - System displays budget vs. actual spending for each category. | 8 |  | 2025-04-14 | 2025-04-20
- System highlights categories that exceed the budget.
US8 | Budget Exceeding Warning | As a user, I want to receive a warning when I exceed my budget so that I can control my spending. | Should Have | Iteration 3 | - System generates a warning message when expenses exceed budget.
[5 empty] | - Users can acknowledge the warning. | 8 |  | 2025-04-21 | 2025-04-25
US9 | Financial Summary Report | As a user, I want to view a financial summary report so that I can analyze my spending patterns. | Could Have | Iteration 4 | - System generates a summary of income, expenses, and budget adherence.
[5 empty] | - Users can filter reports by month or year. | 5 |  | 2025-04-25 | 2025-04-28
US10 | Export Financial Data | As a user, I want to export my financial data to a CSV file so that I can keep a backup. | Should Have | Iteration 4 | - Users can export transactions and budget data to CSV.
[5 empty] | - Exported files can be opened in spreadsheet software. | 8 |  | 2025-04-28 | 2025-05-06
US11 | Input Data Validation | As a user, I want the application to validate my input data so that errors are minimized. | Could Have | Iteration 1 | - System ensures amount is a valid number.
[5 empty] | - System ensures date is in correct format. | 5 |  | 2025-05-06 | 2025-05-12
- System prevents empty category fields.
US12 | Customizable Spending Categories | As a user, I want to be able to customize my spending categories so that they fit my personal needs. | Could ‘ Have | Iteration 4 | - Users can create, edit, and delete categories. | 5 |  | 2025-05-12 | 2025-05-18
- Categories persist after restarting the application.